## Orders
Type of Work | Type Project | Partner | Description | Invoice Number | BAST Value | Status | Submit Date | Return Date | Reason | Resubmit Date | Paid Date
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2,3, and 4Floor HDC Cikarang plus Additional Resource - Payment October 2025 | CUS_INVOICE-2025-11-000001841Project Development | 903765582 | paid | 15 December 2025 |  |  |  | 27 January 2026
Inbound | Project Delta | Internal Consulting Group (ICG) Singapore Pte Ltd | BAST VI.A Phase 2 50% Construction Level 3 & 4 | INV-250908 | 122500 | paid | 08 December 2025 |  |  |  | 06 April 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Termin ke-10 (Oct 2025) Rp 461.446.000 Profesional Fees for testing and commissioning consultancy services for Project NeutraDC 2,3,4 Floor dari total Nilai Kontrak Rp 5.549.594.560 | CMIDO2512077 | 461446000 | paid | 08 December 2025 |  |  |  | 27 January 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2,3, and 4Floor HDC Cikarang plus Additional Resource - Payment September 2025 | CUS_INVOICE-2025-11-000001839Project Development | 903765582 | paid | 15 December 2025 |  |  |  | 27 January 2026
Inbound | Project Delta | Huawei Tech Investment | Description Phase GAC 2 [1.10%) Rp 10.692.000.000 General Contractor MATERIALs For Project Delta Level 3And 4Fit Out Work - Main Long Lead Equipment Arrival on Site - GAC 2 | РТ2529322 | 10692000000 | paid | 15 December 2025 |  |  |  | 05 January 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 2 [0,30%] Rp 2.916.000.000 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Cx2 – LLEC 2 | РТ2534193 | 2916000000 | paid | 15 December 2025 |  |  |  | 20 January 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Final Payment (Nov 2025) Profesional Fees for testing and commissioning consultancy services for Project NeutraDC 2,3,4 Floor | CMIDO2601002 | 298145440 | paid | 15 January 2026 |  |  |  | 12 March 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Payment Desember 2025 - Project Management Consultant (PMC) for 2,3,4 Floor HDC Cikarang, | CUS_INVOICE-2026-01-000000143Project Development | 691821482 | paid | 24 February 2026 |  |  |  | 10 March 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2,3, and 4Floor HDC Cikarang plus Additional Resource - Payment November 2025 | CUS_INVOICE-2025-12-000001989 Project Development | 691821478 | paid | 15 December 2025 |  |  |  | 10 March 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 5 [0,80%] Rp 7.776.000.000 General Contractor MATERIALs For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Arrival on Site – GAC 5 | PT2531931 | 7776000000 | paid | 15 December 2025 |  |  |  | 30 March 2026
Inbound | Project Delta | PT ZTE Indonesia | Term LLEC 7 Payment of the General Contractor (GC) Services for Project Delta Level-2 Fit Out Works - Installation Completion - BUSWAY SYSTEM | ZTE-ID-21052-2025 | 8849683725 | paid | 09 January 2026 |  |  |  | 30 March 2026
Inbound | Project Delta | PT Turner & Townsend | Term Prolongation Tender Rp 365.625.000 Pengadaan Cost Consultant L2, L3, &L4 HDC Cikarang | PRIV00001325 | 365625000 | paid | 07 January 2026 |  |  |  | 25 June 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 12 [6,90%] Rp 67.068.000.000 General Contractor MATERIALS For Project Delta Level 3 And 4 Fit Out Work - Main Long Lead Equipment Arrival on Site - GAC 12 | PT2534262 | 67068000000 | paid | 16 April 2026 |  |  |  | 15 June 2026
Inbound | Project Delta | PT Turner & Townsend | Term Amendment Cost Plan D Rp 224.375.000 Pengadaan Cost Consultant L2, L3, &4L HDC Cikarang | PRIV00001324 | 224375000 | paid | 07 January 2026 |  |  |  | 22 June 2026
Inbound | Project Delta | PT Turner & Townsend | Term Construction Rp 255.000.000 Pengadaan Cost Consultant L2, L3, &L4 HDC Cikarang | PRIV00001326 | 255000000 | paid | 07 January 2026 |  |  |  | 25 June 2026
Inbound | Project Delta | PT ZTE Indonesia | Term GAC 7Payment of the General Contractor (GC) Services for Project Delta Level-2 Fit Out Works - Mani Equipment - BUSWAY SYSTEM | ZTE-ID-21051-2025 | 22233247620 | paid | 15 December 2025 |  |  |  | 30 March 2026
Inbound | Project Delta | PT Pembangunan Perumahan (Persero) Tbk | Termin Ke 2 Pengadaan Structure Enhancement CFRP L3&4 HDC Cikarang | 002/INV/PP/GEDUNG/HDC-II/2025 | 5780000000 | paid | 27 November 2025 |  |  |  | 05 March 2026
Inbound | Project Delta | PT Pembangunan Perumahan (Persero) Tbk | Termin Ke 3 Pengadaan Structure Enhancement CFRP L3&4 HDC Cikarang | 003/INV/PP/GEDUNG/HDC-II/2025 | 5780000000 | paid | 27 November 2025 |  |  |  | 05 March 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 1 [10,30%] Rp 100.116.000.000 General Contractor MATERIALs For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Arrival on Site – GAC 1 -Diesel | PT2534789 | 100116000000 | paid | 08 January 2026 |  |  |  | 16 April 2026
Inbound | Project Delta | PT Mandau Cipta Tenaga Nusantara | Penyelesaian Instalasi - Rp 7.875.000.000 - 45% dari Harga Pekerjaan Pengadaan Instalasi Interkoneksi Tegangan Listrik Menengah Proyek HDC Cikarang | 02/MCTN-TDE/2026 | 7875000000 | review | 07 May 2026
Inbound | Project Delta | PT Mandau Cipta Tenaga Nusantara | Pengadaan Instalasi Interkoneksi Tegangan Listrik Menengah Proyek HDC Cikarang - Termin 1 | 01/MCTN-TDE/2026 | 8750000000 | paid | 30 March 2026 |  |  |  | 28 July 2026
Inbound | Project Delta | Internal Consulting Group (ICG) Singapore Pte Ltd | BAST IV Phase 2 100% Design Completion Level 2 | INV-250902 | 33000 | paid | 16 April 2026 |  |  |  | 13 May 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 7 [3,00%] Rp 29.160.000.000 General Contractor MATERIALs For Project Delta Level 3 And 4 Fit Out Work - Main Long Lead Equipment Arrival on Site - GAC 7 | PT2605826 | 29160000000 | paid | 16 April 2026 |  |  |  | 05 October 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2, 3, and 4 Floor HDC Cikarang (Additional Scope & Extension of Time Level 2, 3, and 4) - Payment May, 2026 | CUS_INVOICE-2026-09-000001610 | 1088529038 | open | 06 October 2026 | Return 1 : 08 Oktober 2026 | jabatan yg di BAST dan di kontrak beda | Resubmit : 09 Oktober 2026
Inbound | Project Delta | PT ZTE Indonesia | Advance Payment for the Contract Regarding Busway for Level 2 and Level 3 Data Hall of Project Delta | ZTE-ID-20704-2026 | 5463625800 | paid | 02 July 2026 |  |  |  | 31 July 2026
Inbound | Project Delta | PT ZTE Indonesia | Term Progress 4 Payment of the General Contractor (GC) Services f o Project Delta Level-2 Fit Out Works - MEP Completion Works | ZTE-ID-21053-2025 | 58312152991 | paid | 30 April 2026 |  |  |  | 09 July 2026
Inbound | Project Delta | PT ZTE Indonesia | 5% Payment of the Total Price L3 Floor in regards with the BAST 1- L3 obtained for the Material on Site Level 3Floor. Contract No. K.TDE.0060/LEG.PRJ/N/2026 dated 21 May 2026 | ZTE-ID-30403-2026 | 6527134350 | open | 10 August 2026
Inbound | Project Delta | PT ZTE Indonesia | 25% Payment of the Total Price L2 Floor in regards with the BAST 2 - L2 obtained for the Installation Completion Level 2 Floor. Contract No. K.TDE.0060/LEG.PRJ/V/2026 dated 21 May 2026 | ZTE-ID-20541-2026 | 3203346500 | open | 10 August 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 5 [0,20%] Rp 1.944.000.000 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work - Main Long Lead Equipment Cx2 - LLEC 5 | PT2626565 | 1944000000 | paid | 13 July 2026 |  |  |  | 05 October 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Termin ke-1 (Sep 2025 - Maret 2026) Rp 3.024.040.000 Profesional Fees for testing and commissioning consultancy services for Project NeutraDC 2,3,4 | CMIDO2607056 | 3024040000 | paid | 13 July 2026 |  |  |  | 15 September 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2, 3, and 4 Floor HDC Cikarang (Additional Scope & Extension of Time Level 2, 3, and 4) - Payment April, 2026 | CUS_INVOICE-2026-09-000001609 | 1088529038 | open | 06 October 2026 | Return : 08 Oktober 2026 | jabatan yg di BAST dan di kontrak beda | Resubmit : 09 Oktober 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2, 3, and 4 Floor HDC Cikarang (Additional Scope & Extension of Time Level 2, 3, and 4) - Payment March, 2026 | CUS_INVOICE-2026-09-000001608 | 1088529038 | open | 06 October 2026 | Return : 08 Oktober 2026 | jabatan yg di BAST dan di kontrak beda | Resubmit : 09 Oktober 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 10[0,40%] Rp 3.888.000.000 General Contractor Services For Project Delta Level 3And 4Fit Out Work - Main Long Lead Equipment Cx2 - LLEC 10 | PT2628917 | 3888000000 | returned | 31 July 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 3 [0,20%] Rp 1.944.000.000 General Contractor Services For Project Delta Level 3 And 4 tFi Out Work - Main Long 1 Lead Equipment Cx2 - LLEC 3 | PT2628755 | 1944000000 | review | 31 July 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | Project Management Consultancy Services for 2, 3, and 4 Floor HDC Cikarang (Additional Scope & Extension of Time Level 2, 3, and 4) - Payment February, 2026 | CUS_INVOICE-2026-09-000001607 | 1088529038 | open | 06 October 2026 | Return : 08 Oktober 2026 | jabatan yg di BAST dan di kontrak beda | Resubmit : 09 Oktober 2026
Inbound | Project Delta | PT ZTE Indonesia | L2 Floor in regards with the BAST 3 - L2 obtained for the Commissioning Completion of Level 2 Floor. | ZTE-ID-31517-2026 | 1281338600 | open | 21 August 2026
Inbound | Project Delta | PT ZTE Indonesia | Term Progress 5A Payment of the General Contractor (GC) Services for Project Delta Level-2 Fit Out Works - Commissioning &Project Completion Works and Al Variation Order Works Completion | ZTE-ID-20626-2026 | 24588439497 | returned | 19 August 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 1 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Cx2 | РТ2628572 | 23328000000 | returned | 19 August 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 4 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Cx2 – LLEC 4 | PT2628762 | 9720000000 | returned | 28 August 2026
Inbound | Project Delta | PT Cushman & Wakefield Indonesia | PMC Services for 2, 3, and 4 Floor HDC Cikarang (Additional Scope & Extension of Time Level 2, 3, and 4) - Payment January, 2026 | CUS_INVOICE-2026-09-000001600 | 1745883848 | open | 06 October 2026 | Return : 08 Oktober 2026 | jabatan yg di BAST dan di kontrak beda | Resubmit : 09 Oktober 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 12 General Contractor Services for Project Delta Level 3 and 4 | PT2628957 | 1234744500 | open | 14 September 2026 | Return 1 : 14 September 2026 Return 2 : 18 September 2026 | Note return 1 : kontrak dan kelengkapan lainnya belum ada Note return 2 : dokumen pendukung lainnya | Resubmit 1 : 15 September 2026 Resubmit 2 : 15 Oktober 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 6b General Contractor Materials for Project Delta level 3 and 4 Fit Out work | PT2628929 | 56376000000 | open | 14 September 2026 | Return 1 : 14 September 2026 Return 2 : 18 September 2026 | Note return 1 : kontrak dan kelengkapan lainnya belum ada Note return 2 : dokumen pendukung lainnya | Resubmit 1 : 15 September 2026 Resubmit 2 : 15 Oktober 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 6a General Contractor Materials for project Delta Level 3 and 4 fit out work | PT2628939 | 83592000000 | open | 14 September 2026 | Return 1 : 14 September 2026 Return 2 : 18 September 2026 | Note return 1 : kontrak dan kelengkapan lainnya belum ada Note return 2 : dokumen pendukung lainnya | Resubmit 1 : 15 September 2026 Resubmit 2 : 15 Oktober 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Termin-4 (June 2026) Fees for testing and commisioning consultacy services for project NeutraDC 2,3,4 Floor | CMIDO2609087 | 605280000 | paid | 15 September 2026 | Return : 15 September 2026 | GR nya belum ada | Resubmit : 17 September 2026 | 22 October 2026
Inbound | Project Delta | Huawei Tech Investment | Huawei GC Services - Phase LLEC 7 | PT2628912 | 6804000000 | open | 29 September 2026 | Return : 01 Oktober 2026 | 1. BA RFA 2. BA Chronology 3. Typo 4. Copy BAST GAC 7 | Resubmit 06 Oktober 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | First Amendment regarding Termin Contract For Procurement of Goods And Services Cx Consultant 2,3,4 floor | CMIDO2608075 | 475344000 | paid | 10 August 2026 |  |  |  | 15 October 2026
Inbound | Project Delta | PT ZTE Indonesia | 5% Payment of the Total Price L2 Floor ni regards with the BAST 1- L2 obtained for the Material on Site Level 2 Floor. Contract No. K.TDE.0060/LEG.PRJ/V/2026 dated 21 May 2026 | ZTE-ID-29540-2026 | 5766023700 | open | 10 August 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 8 [0,60%] Rp 5.832.000.000 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Cx2 – LLEC 8 from Total Contract Rp 972.000.000.000 - SERVICE | PT2613691 | 5832000000 | review | 26 June 2026
Inbound | Project Delta | Huawei Tech Investment | Phase LLEC 9 [0,20%] Rp. 1.944.000.000 General Contractor Services For Project Delta Level 3 And 4 Fit Out Work - Main Long Lead Equipment Cx2 - LLEC 9 | PT2609125 | 1944000000 | paid | 21 May 2026 |  |  |  | 28 September 2026
Inbound | Project Delta | Internal Consulting Group (ICG) Singapore Pte Ltd | BAST V Phase 1 Al Structural Enhancement Design | INV-250904 | 90000 | open | 16 April 2026
Inbound | Project Delta | Internal Consulting Group (ICG) Singapore Pte Ltd | Site Visit Pre-Power On System Check at HDC Cikarang Campus 1 | INV-250901 | 10000 | review | 06 October 2026 | Not return
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 8 [2,30%] Rp 22.356.000.000 General Contractor MATERIALs For Project Delta Level 3 And 4 Fit Out Work – Main Long Lead Equipment Arrival on Site – GAC 8 MATERIAL | PT2611408 | 22356000000 | open | 26 June 2026
Inbound | Project Delta | Huawei Tech Investment | Phase GAC 9 [0,60%] Rp. 5. 832.000.000 General Contractor MATERIALs For Project Delta Level 3 And 4 Fit Out Work - Main Long Lead Equipment Arrival on Site - GAC 9 | PT2605605 | 5832000000 | paid | 21 May 2026 |  |  |  | 28 September 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Termin 5 (July 2026) Additional Work Profesional Fees for consultancy services | CMIDO2609092 | 649680000 | paid | 28 September 2026 | Not return |  |  | 22 October 2026
Inbound | Project Delta | PT Dwimitra Ekatama Mandiri | Pengadaan Temporary HAC - HDC CKR - STAGE 2 | 351/INV/TDE/IX/2026 | 140000000 | open | 28 September 2026 | Return 1 : 02 Oktober 2026 Return 2 : 05 Oktober 2026 | Note Return 1 : sesuaikan PIC Note Return 2 : typo, GR belum ada , diskripsi inv & fp disesuaikan dengan aturan pajak terbaru | Resubmit 1 : 02 Oktober 2026 Resubmit 2 : 15 Oktober 2026
Inbound | Project Delta | PT Dwimitra Ekatama Mandiri | Pengadaan Temporary HAC - HDC CKR - STAGE 1 | 351/INV/TDE/IX/2026 | 140000000 | open | 28 September 2026 | Return 1 : 02 Oktober 2026 Return 2 : 05 Oktober 2026 | Note Return 1 : sesuaikan PIC Note Return 2 : typo, GR belum ada , diskripsi inv & fp disesuaikan dengan aturan pajak terbaru | Resubmit 1 : 02 Oktober 2026 Resubmit 2 : 20 Oktober 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Termin ke-2 (April 2026) Profesional Fees for testing and IDR commissioning consultancy services for Project NeutraDC 2,3,4 Floor | CMIDO2608074 | 649680000 | paid | 10 August 2026 |  |  |  | 15 October 2026
Inbound | Project Delta | PT CommTech (Asia) Ltd | Final payment (Aug 2026) Rp 649.680.000 Additional Work Profesional Fees for testing and commissioning consultancy services for Project NeutraDC 2,3,4 Floor dari total Nilai Kontrak Rp 6.053.704.000 | CMIDO2610105 | 649680000 | open | 20 October 2026 | On Review
Inbound | Project Delta | PT ZTE Indonesia | BAST 2- L3 - Installation Completion Level 3 Floor | ZTE-ID-34158-2026 | 3626185750 | open | 20 October 2026 | On Review